## Slide 1: Project Management tools
BTEC National

## Slide 2: General planning & scheduling tools
Project management software helps you manage the administration, planning and scheduling of your project. You can often use the software charting facilities included in this software to produce graphical versions of your plans.
Project management software has the following features:
Create a task
Store information about a task (e.g. who will do it, how long it will take etc)
Update task information as your project changes
Generate plans based on tasks
Publish charts and reports to help you manage the project and to present information to the stakeholders

## Slide 3: Gantt chart & PERT charts
The common charts are Gantt charts and PERT charts
A Gantt chart is a picture of how long all the tasks should take. You can use Excel to create a Gantt chart

## Slide 4: Gantt chart & PERT charts
The common charts are Gantt charts and PERT charts
A PERT chart (program evaluation and review technique) shows the dependencies between tasks. It depicts the task, its duration and dependency information
20
10
30
40
50
60
T = 1wk
T = 2wks
T = 2wks
T = 4wks
T = 2wks
T = 1wk
T = 1wk
A
E
F
A
C
B
G
D

## Slide 5: Critical Path Methods
Critical path methods identify the minimum time needed to complete a project. They show which tasks are on the critical path. This lets you, as project manager, prioritise these tasks to make the project more likely to finish on time.
Critical path analysis (CPA) works on the principle that some tasks cannot start until previous tasks are finished. For example, you cannot test a program until after you have coded it. you must complete these dependent tasks in a sequence. Often tasks are not dependent on other tasks starting or finishing, so you can do these tasks in parallel.

## Slide 6: Critical Path Methods
Consider this series of tasks for a computer system.
Specify and design system
Code program 1
Test program 1
Code program 2
Test program 2
Test and implement system
The project manager works out the dependencies and timescales and draws up the critical path (shown on next slide). From this you can see that tasks 1, 2, 3 and 6 are on the critical path. A minimum time of 21 days is needed for this project.

## Slide 7: Critical Path Methods
From this you can see that tasks 1, 2, 3 and 6 are on the critical path. A minimum time of 21 days is needed for this project.
Task 1
5 days
Task 2
10 days
Task 3
4 days
Task 6
2 days
Task 5
2 days
Task 4
5 days

## Slide 8: Specialised software packages
To help manage a project there are many packages available. At the simplest, there are freeware or shareware packages available from the Internet. Microsoft Project is a popular middle-of-the-range tool that can help manage a wide variety of projects. For large construction or IT projects involving very many tasks and workers, there is expensive, specialised software available.